## Sheet2 (hidden)
Severity & Priority | Open | Re-Open | Closed | Deferred | Grand Total
High | 35 | 1 | 23 | 3 | 62
Low | 12 | 0 | 0 | 0 | 12
Showstopper | 4 | 1 | 5 | 2 | 12
Grand Total | 51 | 2 | 28 | 5 | 86

## Summary_Consolidated (hidden)
Status | Showstopper |  | High |  | Medium | Low | Grand Total
| Angel | uTrade | Angel | uTrade | uTrade | uTrade
Open | 9 | 5 | 4 | 22 | 6 | 10 | 56
Closed | 2 | 12 | 0 | 37 | 5 | 3 | 59
Deferred | 0 | 6 | 1 | 14 | 0 | 1 | 22
Grand Total | 11 | 23 | 5 | 73 | 11 | 14 | 137

## Summary
uTrade Observations
Status | Showstopper | High | Low | Medium | Grand Total
Open | 6 | 28 | 10 | 8 | 52
Deferred | 6 | 14 | 1 | 0 | 21
Grand Total | 12 | 42 | 11 | 8 | 73
Status | Showstopper |  | High |  | Medium | Low | Grand Total
| Angel | uTrade | Angel | uTrade | uTrade | uTrade
Open | 9 | 6 | 4 | 28 | 8 | 10 | 65
Closed | 2 | 12 | 0 | 37 | 5 | 3 | 59
Deferred | 0 | 6 | 1 | 14 | 0 | 1 | 22
Grand Total | 11 | 24 | 5 | 79 | 13 | 14 | 146

## Observations
Issue no. | Date | Exchange | Segment | Module | Observation Description | Test Data | Steps to Recreate | Severity & Priority | Status | Testing Team Remarks : Angel | Testing Team Remarks : uTrade | Dev Team Status | Dev Team Remarks: uTrade | Business Comments | Reported By | Version | Status by uTrade | ETA by uTrade | Pending At
1 | 28.02.2019 | NA | NA | Server Details | Not able to identify server IP with client log-in Expected Result: System should display IP address at client level under help menu | Client : A81827 | 1. Log-in utrade Application 2. UAT : 172.31.16.189 | High | Closed |  | Can be added as requirement. | Can be done |  | Can be done, Server IP is required? | Nikhil | 1.0.0.0 |  |  | uTrade
2 | 28.02.2019 | NA | NA | Log-in | System allow to log-in multiple session with same Client ID Expected Result: System should not allow to log-in to utrade application with same client ID multiple times | Client : A81827 | 1. Log-in utrade Application 2. Log-in with A81827 3. Again Log-in with same ID | High | Deferred | We will check & confirm | Already reported. |  | Angel Middle-ware does not support this. Already confirmed with Kalpesh. | 03 June Must be done with Angel new library | Nikhil | 1.0.0.0 | done |  | angel
3 | 28.02.2019 | NA | NA | Log-in | System allow to change password with newpassword length less than VARCHAR[6] Expected Result: System should not allow to change password less than VARCHAR[6] length | Client : A81827 | 1. Log-in utrade Application 2. Log-in with A81827 3. Reset Password from Admin 4. Change password from Client EXE | High | Closed | Kindly Refer BRS doc in Jira Story No. AMXTECH - 414 | Password policy request already raised. |  |  | Need API from Angel to get Password policy parameter, only then it can be applied at Front-end | Nikhil | 1.0.0.0 |  |  | uTrade
4 | 28.02.2019 | NA | NA | Log-in | System allow to change password with newpassword length greater than VARCHAR[12] Expected Result: System should not allow to change password greater than VARCHAR[12] length | Client : A81827 | 1. Log-in utrade Application 2. Log-in with A81827 3. Reset Password from Admin 4. Change password from Client EXE | High | Closed | Kindly Refer BRS doc in Jira Story No. AMXTECH - 414 | Password policy request already raised. |  |  | Need API from Angel to get Password policy parameter, only then it can be applied at Front-end | Nikhil | 1.0.0.0 |  |  | uTrade
5 | 01.03.2019 | All | All | Connectivity Status | System is displaying connectivity status as disconnected. If connectivity is disconnected than system should not allow to place order Screen shot attached in Screen shot sheet as "Issue No. 29" Expected Result: System should not allow to place order if connection status is disconnected |  | 1) Log-in with Client ID | Medium | Closed | Remove connectivity status after login. Should display in Help menu after connection Params. | Already known. Remove connectivity status widget from login |  | No API present to detect this. | To be handled at Angel end first, then we will integrate. 11 Apr This widget is removed as of now as discussed. | Nikhil | 1.0.0.0 |  | 2019-04-16 | uTrade
6 | 28.02.2019 | NA | NA | Log-in | System allow to do transaction without changing transaction password Expected Result: System should not allow to place order without transaction password | Client : A81827 | 1. Log-in utrade Application 2. Log-in with A81827 3. Reset Password from Admin 4. Change password from Client EXE | High | Closed |  | Same as Point 5 |  | Password change is taking affect from next log-in. No response is received from Angel Middle-ware for real time change in password. | Need Discussion | Nikhil | 1.0.0.0 |  |  | uTrade
7 | 28.02.2019 | NA | NA | Log-in | System allow to log-in utrade and omnesys application with same client ID Expected Result: System should log-off previous application | Client : A81827 | 1. Log-in utrade Application 2. Log-in with A81827 3. Log-in to omnesys Exe | High | Deferred | We will check & confirm | Same as Point 2 |  | Same as Point 2 | 03 June Must be done with Angel new library | Nikhil | 1.0.0.0 | done |  | angel
8 | 08.03.2019 | All | All | Order Book/Trade Book/ Net Position Filter | System should display orders in Descending order i.e Last placed/ modified order should display first | Client ID : A81827 Exchange : NFO Scrip : RELIANCE 19MAR 1200 PE Qty : 2 lot Order Type : Stop Loss (SL) Product Type = NRML Validity = DAY Price = 88 Trigger Price = 161 | 1) Log-in with Client ID 2) Place Order in NFO 3) Enter Quantity 4) Enter Price 6) Place Order | High | Closed | 30/3/2019 System is displaying randomly any order as first require Last placed/modified order should display first. | QA to check with Vivek for details |  |  | By default, Sorting by time is enabled which will achieve the required use-case. | Nikhil | 1.0.0.0 |  | 2019-04-16 | uTrade
9 | 28.02.2019 | NA | NA | Configuration | Configuration>Lock Workstation System not allow to log-in again even after entering valid password. System allow to quite Expected Result: System should allow to log-in again | Client : A81827 | 1. Log-in utrade Application 2. Log-in with A81827 3. Configuration> Lock workstation 4. Enter Valid Password | High | Closed | Verify and confirm once we received new client exe set up 12.03.19(Nikhil) : Tested and verified working fine | Already reported and fixed. | Done | API from Angel end was awaited for Log-in Authentication , but due to its unavailability , handling was done some other way around. | Done | Nikhil | 1.0.0.0 |  |  | uTrade
10 | 28.02.2019 | NA | NA | Log-in | System allow to change password with only Special Character Expected Result: System should not allow to change password with only special character should display validation message : "Password should be Alphanumeric , With min length 6 CHAR and Max Length 12 CHAR" | Client : A81827 New-password: $$$ Confirm Password : $$$ | 1. Log-in utrade Application 2. Log-in with A81827 3. Reset Password from Admin 4. Change password from Configuration>ChangePassword | High | Closed | Kindly Refer BRS doc in Jira Story No. AMXTECH - 414 | Password policy request already raised. |  |  | Need API from Angel to get Password policy parameter, only then it can be applied at Front-end | Nikhil | 1.0.0.0 |  |  | uTrade
11 | 28.02.2019 | NA | NA | Log-in | System allow to change password with only alphabets Character Expected Result: System should not allow to change password with only alphabets character should display validation message : "Password should be Alphanumeric , With min length 6 CHAR and Max Length 12 CHAR" | Client : A81827 New-password: aaa Confirm Password : aaa | 1. Log-in utrade Application 2. Log-in with A81827 3. Reset Password from Admin 4. Change password from Configuration>ChangePassword | High | Closed | Kindly Refer BRS doc in Jira Story No. AMXTECH - 414 | Password policy request already raised. |  |  | Need API from Angel to get Password policy parameter, only then it can be applied at Front-end | Nikhil | 1.0.0.0 |  |  | uTrade
12 | 28.02.2019 | NA | NA | Log-in | System allow to change password with only "Space character" Expected Result: System should not allow to change password with only space character should display validation message : "Password should be Alphanumeric , With min length 6 CHAR and Max Length 12 CHAR, no space " | Client : A81827 New-password: "abc 123" Confirm Password : "abc 123" | 1. Log-in utrade Application 2. Log-in with A81827 3. Reset Password from Admin 4. Change password from Configuration>ChangePassword | High | Closed | Kindly Refer BRS doc in Jira Story No. AMXTECH - 414 | Password policy request already raised. |  |  | Need API from Angel to get Password policy parameter, only then it can be applied at Front-end | Nikhil | 1.0.0.0 |  |  | uTrade
13 | 28.02.2019 | NA | NA | Log-in | System allow to change password with only small alphabets Character Expected Result: System should not allow to change password with only alphabets character should display validation message : "Password should be Alphanumeric , With min length 6 CHAR and Max Length 12 CHAR and Atleast oneCapital Letter " | Client : A81827 New-password: aaa Confirm Password : aaa | 1. Log-in utrade Application 2. Log-in with A81827 3. Reset Password from Admin 4. Change password from Configuration>ChangePassword | High | Closed | Kindly Refer BRS doc in Jira Story No. AMXTECH - 414 | Password policy request already raised. |  |  | Need API from Angel to get Password policy parameter, only then it can be applied at Front-end | Nikhil | 1.0.0.0 |  |  | uTrade
14 | 28.02.2019 | NA | NA | Log-in | System allows to log-in the same client multiple times in utrade application Expected Result: System should not allowed to log-in the same client id multiple time, it should maintain the sessions | Client : ABL151 Passwodr : abc000 | 1. Log-in with the valid client id & password in the utrade 2. Again open utrade application & log-in with same client id | Showstopper | Deferred | We will check & confirm | Same as Point 2 |  | Same as Point 2 | 03 June Must be done with Angel new library | Suraj | 1.0.0.0 | done |  | angel
15 | 28.02.2019 | NA | NA | Log-in | System not maintaining client session Expected Result: Client should be log out after certain time period (eg. 15 mins) | Client : ABL151 Passwodr : abc000 | 1. Log-in in Utrade exe 2. keep ideal application for 15 mins | High | Deferred | We will check & confirm | Already raised. |  | Angel Middle-ware architecture is connectionless due to which we can’t detect log-out. | 03 June Must be done with Angel new library | Suraj | 1.0.0.0 | done |  | angel
16 | 14.03.2019 | All | All | Market Picture | System does not open market picture (F6) when scrip focus is changed using up and down arrow keys. same is working fine with left click of mouse and F6 Expected Result : Market picture should open when focus on scrip changed using up and down arrow key | NA | 1) Log-in with Client ID 2) Go to market watch 3) Select Scrip using up and down arrow key 4) Press F6 | High | Closed |  |  |  |  | Done | Nikhil | 1.0.0.0 |  | 2019-04-16 | uTrade
17 | 28.02.2019 | NA | NA | Configuration | Configuration>Change Password System not allow to change password getting message : "Password does not match" second time Expected Result: System should allow to change password from configuration > Change password every time | Client : A81827 | 1. Log-in utrade Application 2. Log-in with A81827 3. Configuration>Change Password | High | Closed | Verify and confirm once we received new client exe set up 12.03.19 (Nikhil) : Tested and verified working fine | Already reported and fixed. |  |  | Done | Nikhil | 1.0.0.0 |  |  | uTrade
18 | 28.02.2019 | NSE | EQ | BUY/SELL Window | System should not display Order Type as: LimitOrder /MarketOrder/Stop Limit/Stop Expected Result: System should display : Limit, Market, SL-Limit, SL-Market | Client : A81827 | 1. Log-in utrade Application 2. Go to Market Watch 3. (F1.Open Buy Order screen 4. Select Order Type dropdown | High | Deferred | 30/3/2019 As per BRS require Text name as Limit, Market, SL-Limit and SL-Market Kindly refer AMXTECH - 91 story in JIRA | This is working fine at our end. Need to confirm the exact case executed by client. |  |  | We have implemented this as suggested by Point #23 of last sheet, details: System displayed Order Type (Dropdown list) as "Stop" in the Buy/ Sell Order window Expected Result: System should displayed proper order type in the dropdown list as "Stop Loss Limit" & "Stop Loss Market" 03 June done as discussed | Nikhil | 1.0.0.0 | done |  | angel
19 | 28.02.2019 | NA | NA | Market Watch | System should displayed Market (dropdown option) label as Exchange Expected Result: In utrade, in all windows "Market" label should be displayed Exchange |  | 1. Log-in utrade 2. Books -> Market Watch -> Default Market Watch | High | Deferred | 30/3/2019 Kindly refer AMTECH - 94 story in JIRA | Already known. Can be added as requirement. |  |  | TBD with ui/ux changes in July | Suraj | 1.0.0.0 |  | Ph-2 | uTrade
20 | 28.02.2019 | NA | NA | Market Watch | System displayed selected columns in the .csv file while Export to Excel from watchlist following columns displayed in .csv file SOURCE, MARKET, SCRIP CODE, SYMBOL, SYMBOL NAME Expected Result: System should displayed all the columns in the .CSV file while Export to xls from Market Watch |  | 1. Log-in utrade 2. Books -> Market Watch -> Default Market Watch 3. Right click on Market Watch & select Export to xls option | High | Deferred | 30/3/2019 Kindly refer AMTECH - 94 story in JIRA | Already known. Can be added as requirement. |  |  | 03 June Behaviour is like this only. Angel team will get back | Suraj | 1.0.0.0 |  | NA | angel
21 | 28.02.2019 | NA | NA | BUY/SELL Window | F1 , F2, + , - key are not working on the Dashboard Expected Result: System should opened buy or sell order window |  | 1. Close all the windows if opened on the dashboard 2. Press F1 or F2 or '+' or '-' key | High | Deferred | Here dashboard means, log-in into exe, close all the open window and press F1, F2, + or - e.g. without Market Watch | Not clear about Dashboard according to client terminologies. Need to ask client regarding the same. |  |  | Requirment: Need significant effort Need discussion. 03 June will do as per understanding & discusion | Suraj | 1.0.0.0 |  | Ph-2 | uTrade
22 | 28.02.2019 | NA | NA | BUY/SELL Window | System displayed Buy / Sell order window title as "Single Buy Order" and "Single Sell Order" Expected Result: System should displayed Buy Order & Sell Order window title for respective Order Window |  | 1. Open Market Watch, Select a Symbol & press F1 or F2 key | High | Deferred | Verify and confirm once we received new client exe set up 30/3/2019 Issue still persist Minor change can be done in next interim Exe Just need to change the text name in Open window of order form from Single order window to Buy and Sell Order | Can be added as requirement. |  |  | 03 June title is also showing single order | Suraj | 1.0.0.0 |  | June | uTrade
23 | 28.02.2019 | All | All | Order Report | System allowed only few columns to filter the order report Expected Result: System should allowed to filter all the columns in the order report | Client : ABL151 Passwodr : abc000 | 1. Log-in in utrade 2. Place a order 3. Go to Order report 4. Right click on the Order Report & Select Filter option | High | Deferred | This is not the new requirement. This is basic functionality. Refer attached BRS in Jira Story No. AMXTECH-89 30/3/2019 As per product filter it is working but as per BRS will be closed in phase 2 | Already known. Can be added as requirement. |  |  | Requirment, To be taken in Phase-2 Product filter is added in all Books. 03 June: List of columns needed form angel. | Suraj | 1.0.0.0 |  | Ph-2 | uTrade
24 | 28.02.2019 | All | All | Margin Summary | System displayed Fund View label as "Margin Summary" Expected Result: Margin Summary option should be displayed as "Fund View" |  | 1. Go to Books -> Margin Summary | High | Closed | Verify and confirm once we received new client exe set up | Can be added as requirement. | In progress |  | Done | Suraj | 1.0.0.0 |  |  | uTrade
25 | 28.02.2019 | All | All | Order Depth | System should allow to open buy or sell options from Order Depth window. Expected Result: System should open Buy or Sell window after pressing F1 or F2. |  | 1. Open Market Watch, Add EQ symbol 2. Open order depth 3. Select the symbol & press F1 or F2 key to place order | High | Closed | Verify and confirm once we received new client exe set up | Already known. Can be added as requirement. |  |  | To be Done | Suraj | 1.0.0.0 |  |  | uTrade
26 | 28.02.2019 | All | All | Market Watch | System is allowing to hide all columns in Market watch. Expected Result: System should not allow to remove all columns and display default column like Symbol, Series Exchange etc. System should display validation or confirmation message before removing all columns. |  | 1. Open Market Watch 2. Right click on Market Watch and select Hide / Show column 3. Remove tick from Select All option. 4. Click on OK | High | Deferred | This is not the new requirement. This is basic functionality. Refer attached BRS in Jira Story No. AMXTECH-94 30/3/2019 Default column mention in BRS which cannot be hided or removed | Already known. Can be added as requirement. |  |  | Will do this. But this is not mentioned in the mentioned BRS. 03 June To be done as discussed | Suraj | 1.0.0.0 |  | Ph-2 | uTrade
27 | 14.03.2019 | All | All | Market Picture | System does not display strike price in Ascending order market picture (F6) for option contracts | Client ID : A81827 Exchange : NSEFO Scrip : TCS19MAR 200CE | 1) Log-in with Client ID 2) Go to market watch 3) Select Scrip 4) Press F6 5) Select Strike price dropdown | Low | Closed |  |  |  |  | Done | Nikhil | 1.0.0.0 | Open | 2019-04-16 | uTrade
28 | 05.03.2019 | NFO | FUTIDX | Order Placement | System allow to place FNO order in product type Margin Expected Result : System should not allow to place order in Margin product type and should display product type Carry forward and Intraday for FNO Segment | Client ID : A81827 Exchange : NFO Scrip : BANKNIFTY 19MAR FUT Qty : 20 Product Type = CNC | 1) Log-in with Client ID 2) Place Order in FNO 3) Select Product type Margin | High | Deferred | 30/3/2019 Kindly refer AMTECH - 91 story in JIRA |  |  |  | Pending at Angel-end middle layer. Already caltured on mail. Same as showstopper issue # 34 03 June Discussion needed between Sahil & Kalpesh | Nikhil | 1.0.0.0 |  | TBD | angel
29 | 05.03.2019 | NFO | FUTIDX | Order Placement | System allow to place FNO SL/SL-M Order with validity type = IOC Expected Result : System should not allow to place SL/SL-M Order with validity type IOC | Client ID : A81827 Exchange : NFO Scrip : BANKNIFTY 19MAR FUT Qty : 20 Product Type = NRML Order Type = SL/SL-M | 1) Log-in with Client ID 2) Place Order in FNO 3) Select Product type 4) Select Order Type | Showstopper | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
30 | 05.03.2019 | NSE | EQ | Order Placement | System does not fetched Disclosed Qty for Order Modification Expected Result : System should display prefetched value of disclosed quantity for BSE-EQ/NSE-EQ/CDS/MCX/NCDEX | Client ID : A81827 Exchange : NSE Scrip : TCS Qty : 100 Disc Qty : 50 Product Type = NRML Validity = DAY Modify Disc Qty = 70 | 1) Log-in with Client ID 2) Place Order in NSE-EQ 3) Select Product type 4) Select Order Type 5) Enter Qty/Disc Qty 6) Modify Disc Qty | Showstopper | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
31 | 05.03.2019 | NSE | EQ | Order Book | System does not display disclosed Qty column Expected Result : System should display disclosed qty in Order book column | Client ID : A81827 Exchange : NSE Scrip : TCS Qty : 100 Disc Qty : 50 Product Type = NRML Validity = DAY | 1) Log-in with Client ID 2) Place Order in NSE-EQ 3) Select Product type 4) Select Order Type 5) Go to Order Book | High | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
32 | 05.03.2019 | NSE | EQ | Order Placement | System does not calculate Disclosed quantity value if disc %= 20 is entered in Order form Settings Expected Result : System should calculate disclosed quantity value based on Disc Qty percentage define in Order form settings | Client ID : A81827 Exchange : NSE Scrip : TCS Qty : 100 Disc Qty : 50 Product Type = NRML Validity = DAY | 1) Log-in with Client ID 2) Place Order in NSE-EQ 3) Select Product type 4) Select Order Type 5) Go to order form settings 6) Enter Disc Qty % = 20 | High | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
33 | 05.03.2019 | All | All | Trade Book | System does not allow to do position conversion from Trade book/Net position window Expected Result : System should allow position conversion | Client ID : A81827 Exchange : NSE Scrip : TCS Qty : 100 Traded Qty: 50 Product Type = NRML Validity = DAY | 1) Log-in with Client ID 2) Place Order in NSE-EQ 3) Select Product type 4) Select Order Type 5) Go to Net position 6) Covert position from NRML to MIS | Showstopper | Deferred | We have reported this issue to OMNESYS |  |  |  | 03 june To be handled at NP only | Nikhil | 1.0.0.0 |  | June | uTrade
34 | 05.03.2019 | NSE | EQ | Order Placement | System allow to place order in NRML product type as for NSE/BSE Cash segment Expected Result : System should not allow to place order in NRML product type and should display Margin, Intraday and Delivery product type for Cash segment |  | 1) Log-in with Client ID 2) Place Order inNSE / BSE | Showstopper | Deferred | 30/3/2019 It is not fessible in User profile API So we will discuss on same and provide you a different API for dealer in which dealer will have information about product and segment of client |  |  |  | uTrade: Raised request to get these info per client, per exchange in UserProfile API, but that was not done by Angel team Ref: User Profile API gives Mapped Exchange List and Products list for a Client i.e. Client -> Exchange List and Product List. But , Exchange-Product mapping is not being received as received in LoginRespone i.e. Client + Exchange -> Product. From mail: C API Analysis & Issues ¦¦ Jan 2019 As discussed with Kalpesh, he will get back on the availability of the API. As discussed with Priyank the name of the Products will be handled at Angel's middle layer 03 June Discussion needed between Sahil & Kalpesh | Nikhil | 1.0.0.0 | Open at Angel | TBD | angel
35 | 05.03.2019 | NSE | EQ | Order Book | System is display ing Order Status CONFIRMED in order book Expected Result : System should display Order Status OPEN in order book Order Status : 1) CONFIRMED = OPEN 2) NEW REJECTED = REJECTED 3) CANCELED = CANCELED 4) AMO CANCELED = canceled after market order 5) Pending orders = open pending 6) Cancel order pending = Cancel pending Trade Book : 1) FILLED = COMPLETE | Client ID : A81827 Exchange : NFO Scrip : BANKNIFTY 19MAR FUT Qty : 20 Product Type = CNC | 1) Log-in with Client ID 2) Place Order in FNO 3) Select Product type CNC 4) Go to order book 5) Verify Order Status | High | Deferred | 30/3/2019 Kindly refer AMTECH - 89 story in JIRA |  |  |  | Requirment, To be taken in Phase-2 03 June. Nomenclatures to be changed once for all with other points as well. | Nikhil | 1.0.0.0 |  | Ph-2 | uTrade
36 | 05.03.2019 | All | All | Order Book | System does not display Executed orders in the Order Book Expected Result : System should displayed all the Pending, Traded / Partially Traded Orders in the Order Book All - All Order will display Pending - Only Pending order will display  Unconfirmed - Only Unconfirmed order like Ximitted will display  Executed - Only Executed order will display  Canceled - Only Canceled order will display  Rejected - Only Rejected order will display | Client ID : ABL152 Exchange : BSE Scrip : TCS Qty : 100 Product = CNC Order Type = Market Order | 1) Log-in with Client ID 2) Open Order window from the Market Watch 3) Type Qty 4) Select Order Type & Product 5) Place Order (Order Should be Fully Executed) 6) Open Order Book | High | Deferred | 30/3/2019 Kindly refer AMTECH - 89 story in JIRA |  |  |  | Requirment, To be taken in Phase-2 03 June Dupiicate, all orders to be displayed in OB | Suraj | 1.0.0.0 | duplicate |  | angel
37 | 05.03.2019 | All | All | Net Position | In Net Position, System displayed amount with the 6 decimal places instead of 4 Decimal places e.g. Avg Buy Price, Avg Sell Price, Buy Amount, Sell Amount, Net Price, Net Value, M2M P/L, Booked P/L, Net P/L columns Expected Result : System should displayed precision up to 4 decimal places in the Net Positions | Client ID : ABL152 Exchange : BSE Scrip : ACC Qty : 78 Product = CNC Order Type = Market Order | 1) Log-in with Client ID 2) Open Order window from the Market Watch 3) Type Qty 4) Select Order Type & Product 5) Place Order (Order Should be Fully Executed) 6) Open Net Position | High | Closed | [5 empty] | Suraj | 1.0.0.0 |  |  | uTrade
38 | 05.03.2019 | All | All | Order Placement | System does not allowed to place disclose quantity along with stop loss Limit & stop loss Market order. While selecting Order Type as Stop or Stop Limit, Dis Qty field get disabled Expected Result : System should allowed to place dis qty along with the Stop Loss Limit & Stop Loss Market order in all the segments Except NSE Futures & options |  | 1) Log-in with Client ID 2) Open Order window from the Market Watch 3) Select Order Type as Stop or Stop Limit | Showstopper | Closed | [5 empty] | Suraj | 1.0.0.0 |  |  | uTrade
39 | 6.03.2019 | All | All | Order Book | System displayed multiple orders in Rejection History Book after Order Cancellation from order book Expected Result : System should displayed only single order entry in the Rejection History tab after cancel the order | Client ID : ABL152 Exchange : BSE Scrip : ACC Qty : 78 Price : 101 Product = CNC Order Type = Limit Order | 1) Log-in with Client ID 2) Open Order window from the Market Watch & Place Order 3) Order should be displayed in the order book (with Confirmed Status) 4) Cancel the same order 5) Verify Rejected History tab | High | Closed | [5 empty] | Suraj | 1.0.0.0 |  |  | uTrade
40 | 07.03.2019 | NSE | Cash | Order Book | System is not allow to cancel order getting error : Order Not found | Client ID : A81827 Exchange : BSE Scrip : ABBOTINDIA Qty : 15 Product Type = NRML Validity = DAY Price = 7500 | 1) Log-in with Client ID 2) Place Order in NSE EQ 3) Enter Quantity 4) Enter Disc Qty 5) Select Product type 6) Select Validity 7) Cancel Order | High | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
41 | 18.03.2019 | Log-in | All | Log-in | System does not retain client ID Expected Result : System should retain client ID on second time log-in client id should be pre populated | Client ID : A81827 | 1) Log-in with Client ID 2) log out and log-in again | Medium | Closed |  |  |  |  | Done | Nikhil | 1.0.0.0 |  | 2019-04-16 | uTrade
42 | 07.03.2019 | NSE | CDS | Order placement | System does not display price and trigger price correctly (Price= 80002.5000 and trigger price = 80250.0000) Expected Result : System should display price and trigger price in multiple of tick size | Client ID : A81827 Exchange : CDS Scrip : EURINR 19MARFUT Qty : 2 Order Type : SL Product Type = NRML Validity = DAY Price = 82.5000 Trigger Price = 83.0000 | 1) Log-in with Client ID 2) Place Order in NSE EQ 3) Enter Quantity 4) Enter Disc Qty 5) Select Product type 6) Select Validity 7) Place Order | High | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
43 | 07.03.2019 | NSE | NFO | Order Book | System does not update modify quantity after order modification in NFO segment required to logout-login | Client ID : A81827 Exchange : NFO Scrip : STAR 19MAR FUT Qty : 20 Product Type = NRML | 1) Log-in with Client ID 2) Place Order in NSE EQ 3) Enter Quantity 4) Enter Disc Qty 5) Select Product type 6) Select Validity 7) Place Order | High | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
44 | 07.03.2019 | All | All | Logout | System does not allow to log-out form application it is abruptly closing the application Expected Result : System should provide log-out option and than allow to exit ( Should ask for confirmation message "Do you want to log-out from application?") | NA | 1) Log-in with Client ID 2) Click on Exit | Showstopper | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
45 | 18.03.2019 | All | All | Order placement | System does not highlight field for which error is occurred, System display error "limit price should not be 0" after clicking ok cursor is getting highlight to submit button | Client ID : A81827 Exchange : MCX Scrip : GOLD 19MAR FUT Validity : GTD Order Type : SL (Sell Order) Price = 0 | 1) Log-in with Client ID 2) Place Order with limit price = 0 | Medium | Open | As discussed with Sumit, will do during UX/UI design (04-Apr-2019) |  |  |  | Requirment: Need significant effort. Can be done with new ui/ux 03 June Cursor should go to the field which is showing error. | Nikhil | 1.0.0.0 |  | Ph-2 | uTrade
46 | 08.03.2019 | NSE | NFO | Order placement | System allow to place/modify Stop loss order even if trigger price is out of circuit limit Expected Result : System should display check circuit limit rejection if trigger price is out of circuit limit | Client ID : A81827 Exchange : NFO Scrip : RELIANCE 19MAR 1200 PE Qty : 2 lot Order Type : Stop Loss (SL) Product Type = NRML Validity = DAY Price = 88 Trigger Price = 161 Lower Circuit limit = 10.1 Upper Circuit limit = 158.1 | 1) Log-in with Client ID 2) Place Order in NFO 3) Enter Quantity 4) Enter Price within Crt Limit = 88 5) Enter Trigger Price out of crt limit = 161 6) Place Order | Showstopper | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
47 | 20.03.2019 | All | All | Connection Parameters | In connection Parameter Provide status of UDP ot TCP port : Connected or Disconnected instead of displaying number | NA | 1) Log-in with Client ID 2) Go to help 3) Connection Parameters | Medium | Closed |  |  |  |  | Done. Connected / Disconnected string is added based on the status. | Nikhil | 1.0.0.0 | Open | 2019-04-16 | uTrade
48 | 11.03.2019 | BSE | EQ | Order placement | System is not displaying Validity type EOS Expected Result : For BSE - EQ system should display validity DAY/IOC/EOS | Client ID : A81827 Exchange : BSE Scrip : TCS Order Type = Stop Loss Price = 2000 Tr. Price = 1980 Qty = 2 Disc Qty = 1 Validity = EOS Product Type = NRML | 1) Log-in with Client ID 2) Place Order in BSE 3) Enter Quantity 4) Enter Disc Qty 5) Enter Price 6) Enter Tr. Price 7) Place Order | High | Closed | [5 empty] | Nikhil | 1.0.0.0 | Done | March-end | uTrade
49 | 11.03.2019 | NSE | NFO | Order placement | 1) "Date" text should be renamed to "Expiry Date" 2) "Option Mode" text should be "Option Type" 3) "Instrument Type" text should be "Instrument Name" | Client ID : A81827 Exchange : NFO Scrip : TCS 19MAR 2000 CE Order Type = Stop Loss | 1) Log-in with Client ID 2) Place Order in NFO 3) Enter Quantity 4) Enter Disc Qty 5) Enter Price 6) Enter Tr. Price 7) Place Order | Low | Deferred | 30/3/2019 Kindly refer AMTECH - 91 story in JIRA |  |  |  | Requirment, To be taken in Phase-2 03 June To be done with nomenclature changes | Nikhil | 1.0.0.0 |  | ph-2 | uTrade
50 | 20.03.2019 | All | All | Books>Indices | System is not displaying indices values on real time basis for all segment Eg: BSE - Sensex ,MCX - MCXCOMDEX | NA | 1) Log-in with Client ID 2) Go to Books 3) Go to indices 4) Select market 5) Select Symbol 6) verify Indices | High | Closed | 09/04/2019 Application is not displaying any data / values. |  |  |  | Done | Nikhil | 1.0.0.0 | Open | 2019-04-16 | uTrade
51 | 20.03.2019 | All | All | Configuration | System lock the application before set time in Configuration > General setting > Lock work station timer (15 min) . Not able to identify timer is in (sec, min etc) | NA | 1) Log-in with Client ID 2) Configuration > General setting > Lock work station timer (15 min) 3) Verify lock workstation timer | High | Closed |  |  |  |  | Label of unit is added. | Nikhil | 1.0.0.0 | Open | 2019-04-16 | uTrade
52 | 13.03.2019 | NSE | NFO | Order placement | System does not allow to modify validity from Day to IOC for Put option Index contracts Expected Result : System should allow to modify validity from Day to IOC and should Cancel/Trade IOC order | Client ID : A81827 Exchange : NFO Scrip : NIFTY 19MAR 11000 PE | 1) Log-in with Client ID 2) Select BANKNIFTY 109MAR 27000 CE scrip in market watch 3) Press F1/F2 on scrip | High | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
53 | 20.03.2019 | All | All | Order Placement | System should not allow to reset all the fields while modifying the open order from order book Expected Result : In the Modify Order form "Reset" option should be worked only for Qty , Dis Qty, Price & Stop loss price fields | Client ID : A81827 Exchange : MCX Scrip : GOLD 19MAR FUT Validity : GTD Order Type : SL (Sell Order) Price = 32,000 Tr.Price = 31500 | 1) Log-in with Client ID 2) Open Order book 3) Select open order 4) Right Click and modify order 5) Reset Order | High | Closed |  |  |  |  | Reset button is removed in modification case, as mutually discussed with Vivek. | Nikhil | 1.0.0.0 |  | 2019-04-16 | uTrade
54 | 20.03.2019 | All | All | Order Book | Verify the sorting of order in order book for all field Expected : System should sort orders as per the field selected for sorting |  |  | Medium | Open | 4/4/19 Sorting is working only on Symbol field and required on below mention fields Symbol Order Id Exchange Order id Product type Order type Date&time |  |  |  |  | Nikhil | 1.0.0.0 |  | Ph-2 | uTrade
55 | 20.03.2019 | All | All | Trade Book | System should display counts on trade book for traded order and same is applicable for Rejection order also |  |  | Medium | Closed |  |  |  |  | Done | Nikhil | 1.0.0.0 |  | 2019-04-16 | uTrade
56 | 14.03.2019 | MCX | FUTCOM | Order placement | System display "Is Triggered " status as "NO" in order book for SL -Sell order in order book Expected Result : System should display "Is triggered" status as Yes in order book | Client ID : A81827 Exchange : MCX Scrip : GOLD 19MAR FUT Validity : GTD Order Type : SL (Sell Order) Price = 32,000 Tr.Price = 31500 | 1) Log-in with Client ID 2) Select GOLD 19MAR FUT 3) Press F2 on scrip 4 ) Select Validity = DAY 5) Select Order Type = SL | High | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
57 | 14.03.2019 | All | All | Holding | System does not display Holding value in Holding portfolio Getting error : "Internal error occurred while adding row" | Client ID : A81827 Exchange : NSE Scrip : TCS Qty : 100 | 1) Log-in with Client ID 2) Go to books 3) Click on Holding portfolio 4) Verify uploaded holding from nest trader | High | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
58 | 22.03.2019 | All | All | Market watch | Following drop down should be in Ascending Order: Market drop down : Should be in alphabetical sequence Option Type : Should be in alphabetical sequence E.g CE,PE | NA | 1) Log-in with Client ID 2) Go to market watch | Low | Open |  |  |  |  | will do | Nikhil | 1.0.0.0 |  | Ph-2 | uTrade
59 | 22.03.2019 | All | All | Order placement | Following drop down should be in Ascending Order: (Buy /Sell Screen) : Product type : Should be in alphabetical Sequence (Buy /Sell Screen) : Expiry Date : Date should be in ascending order for option contract (Buy /Sell Screen) : Option Mode should be in alphabetical order | NA | 1) Log-in with Client ID 2) Place order in NFO 3) Select option Contract | Low | Open |  |  |  |  | will do | Nikhil | 1.0.0.0 |  | Ph-2 | uTrade
60 | 14.03.2019 | MCX | FUTCOM | Order placement | System does not allow to place square off order from Net position screen for MCX Order getting error : " Invalid product type" | Client ID : A81827 Exchange : MCX Scrip : GOLD 19MAR FUT Validity : GTD Order Type : SL (Sell Order) Price = 32,000 Tr.Price = 31500 | 1) Log-in with Client ID 2) Go to Net position 3) Right Click > Square off | High | Closed | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
61 | 22.03.2019 | All | All | Order Book | Following drop down should be in Ascending Order: Order Book > "Status" filter should be in alphabetical sequence Order Book > "Market" filter should be in alphabetical sequence | NA | 1) Log-in with Client ID 2) Go to Books 3) Select Order Book | Low | Open |  |  |  |  | will do | Nikhil | 1.0.0.0 |  | Ph-2 | uTrade
62 | 18.03.2019 | All | All | Order placement (AMX server down) | System does not store orders in queue Expected result : Once the server connection is up system should place order from queue | NA | 1) Log-in with Client ID 2) Place order when AMX server is down | High | Closed |  |  |  |  | This is not a Front-end responsibility | Nikhil | 1.0.0.0 |  |  | uTrade
63 | 22.03.2019 | All | All | Trade Book | Following drop down should be in Ascending Order: Trade Book >"Market" filter should be in alphabetical sequence Trade Book >"Instrument Type" filter should be in alphabetical sequence Trade Book >"Option Type" filter should be in alphabetical sequence | NA | 1) Log-in with Client ID 2) Go to Books 3) Select Trade Book | Low | Open |  |  |  |  | will do | Nikhil | 1.0.0.0 |  | Ph-2 | uTrade
64 | 22.03.2019 | All | All | Net Position | Following drop down should be in Ascending Order: Net position >"Market" filter should be in alphabetical sequence Net position>"Instrument Type" filter should be in alphabetical sequence Net position >"Option Type" filter should be in alphabetical sequence | NA | 1) Log-in with Client ID 2) Go to Books 3) Select Net position | Low | Open |  |  |  |  | will do | Nikhil | 1.0.0.0 |  | Ph-2 | uTrade
65 | 22.03.2019 | All | All | Market Picture | Following drop down should be in Ascending Order: Market Picture > "Instrument Type" filter should be in alphabetical sequence (Future , Option ) Market Picture > "Strike Price" filter should be in ascending order for option contract | NA | 1) Log-in with Client ID 2) Open Market Picture | Low | Open |  |  |  |  | will do | Nikhil | 1.0.0.0 |  | Ph-2 | uTrade
66 | 22.03.2019 | All | All | Rejection History | Following drop down should be in Ascending Order: Rejection History > "Market" filter should be in alphabetical sequence Rejection History > "Order Status" filter should be in alphabetical sequence Rejection History > "Option Type" filter should be in alphabetical sequence | NA | 1) Log-in with Client ID 2) Open Rejection History | Low | Open |  |  |  |  | will do | Nikhil | 1.0.0.0 |  | Ph-2 | uTrade
67 | 20.03.2019 | BSE | EQ | Holding | System is not displaying holding for different series Eg. EDUEXEL - XT series stock getting error " Internal error occurred while adding row" | NA | 1) Log-in with Client ID 2) Update Holding from NT 3) Select different series symbols E.g ( EDUEXEL - XT) 4) Go to Books of utrade 5) Go to holding portfolio | Showstopper | Closed |  |  |  |  | uTrade team is checking | Nikhil | 1.0.0.0 | Done | March-end | uTrade
68 | 28.02.2019 | NA | NA | Log-in | System allow to log-in without changing password Expected Result: System should not launch utrade application before changing password | Client : A81827 | 1. Log-in utrade Application 2. Log-in with A81827 3. Reset Password from Admin 4. Change password from Client EXE 5. Close change password | High | Open | 09/04/2019 Remove Close (X) icon, application should not allow to close change password window without changing password. At first time login or after reset password from admin | Already reported. |  | To be Done Post March | 03 June, Discussed will be done. Change pwd will be prompted before the app is actually logged-in | Nikhil | 1.0.0.0 |  | June | uTrade
69 | 28.02.2019 | NA | NA | Log-in | System not allow to reset password using forgot password Expected Result: System should allow to reset password and send it to register email/mobile | Client : A81827 | 1. Log-in utrade Application 2. Log-in with A81827 3. Click on forgot password 4. Enter Email/PAN/mobile 5. Reset password | High | Open | 4/4/19 Hasrish will confirm the same and will let us know | Yet in QA. |  | Service for Email/SMS is not working at Angel/Omnesys end , already raised a concern for the same. | Service for Email/SMS is not working at Angel/Omnesys end , already raised a concern for the same. | Nikhil | 1.0.0.0 |  | Angel to revert | Angel
70 | 28.02.2019 | NA | NA | Password Expiry Message | System not displaying password expiry message Expected Result: System should display password expiry message : "Your password will expire in next 60 days" | Client : A81827 New-password: "abc123" Confirm Password : "abc123" | 1. Log-in utrade Application 2. Log-in with A81827 3. Reset Password from Admin 4. Change password from Configuration>ChangePassword | Medium | Open | Kindly Refer BRS doc in Jira Story No. AMXTECH - 414 22-3-19 After log-in utrade "Your Password will expire in 0 days" displayed. | Password policy request already raised. |  |  | Done.Backend only send non-zero value before 3 days so this will be displayed only before 3 days of expiry. This is not tested at our end, raised concern to Angel team separately. 03 june it's already delivered in Phase-1, nothing is pending at uTrade end. | Nikhil | 1.0.0.0 | done |  | angel
71 | 07.03.2019 | NSE | Cash | Order placement | System does not allow to place order in validity type COL | Client ID : A81827 Exchange : NFO Scrip : TCS 19MARCH FUT Qty : 500 Product Type = NRML Validity = COL Price = 1820 | 1) Log-in with Client ID 2) Place Order in NSE FNO 3) Enter Quantity 4) Enter Disc Qty 5) Select Product type 6) Select Validity | High | Deferred | 4/4/19 This issue is already raised to Omnesys and expected to get resolve in mid april 2019 release by Omnesys. |  |  |  | Pending at Angel-end middle layer. Already caltured on mail. 03 June: As per mailchain: Angel API issues ¦¦ 02 March this is still pending at Angel end | Nikhil | 1.0.0.0 |  | void | angel
72 | 08.03.2019 | All | All | Order placement | Tab Key function is not working: System should allow to select Option type Validity Strike price Order type Product type dropdown value after selecting using down arrow key and tab key Expected Result : System should allow to select drop down value using Tab key | Client ID : A81827 Exchange : NFO Scrip : RELIANCE 19MAR 1200 PE Qty : 2 lot Order Type : Limit Product Type = NRML Validity = DAY Price = 18 | 1) Log-in with Client ID 2) Place Order in NFO 3) Enter Quantity 4) Enter Disc Qty 5) Select Order type (ALT +Down arrow Key) 6) Select Stop loss order 7) Press TAB Key | High | Open | 30/3/2019 Kindly verify tab key function for all drop down for All segment in order entry form. It is working only for symbol drop down. |  |  |  | 03 June As per discussion, Alt +Down arrow should work for all dropdowns | Nikhil | 1.0.0.0 | Open | TBD | uTrade
73 | 11.03.2019 | NSE | NFO | AMO Order placement | System does not allow to place AMO | Client ID : A81827 Exchange : NFO Scrip : TCS 19MAR 2000 CE Order Type = Stop Loss | 1) Log-in with Client ID 2) Place AMO | Showstopper | Open | As discussed with Sumit, discussion required with Prod Team (04-Apr-2019) |  |  |  | AMO was not in Phase-1. It's not just enabling in Order form, It would have impact on Order book etc as well. Please share details / BRD of the same to be planned in future releases. | Nikhil | 1.0.0.0 |  | TBD | uTrade
74 | 12.03.2019 | All | All | Market Watch | System allow to enter same scrip multiple times in market watch Expected Result : System should not allow to add multiple times same scrip It should highlight focus to available scrip | Client ID : A81827 Exchange : NFO Scrip : TCS 19MAR 2000 CE | 1) Log-in with Client ID 2) Go to market watch 3) Add scrip 4) Add same scrip multiple times | Low | Closed | 30/3/2019 Kindly refer AMTECH - 94 story in JIRA As discussed with Sumit, need discussion with Product Team (01-Apr-2019) As discussed with Alpesh, uTrade will do necessary changes |  |  |  | This is done to make multiple pairs in MW, can be made configurable. Need Discussion 11 Apr As discussed with Alpesh, Priyank. uTrade it making this feature (Duplicate entry) configurable | Nikhil | 1.0.0.0 |  | 2019-04-16 | uTrade
75 | 14.03.2019 | MCX | FUTCOM | Order placement | System does not display Validity type GTD,GTC, Expected Result : System should display Validity DAY,IOC,GTD,GTC, ,EOS for MCX and NCDEX exchange segments. GTD date should be enable on selection of validity type GTD | Client ID : A81827 Exchange : MCX Scrip : ALUMINIUM 19MAR FUT Validity : GTD | 1) Log-in with Client ID 2) Select ALUMINIUM 19MAR FUT 3) Press F1/F2 on scrip 4 ) Select Validity = GTC 5) Enter GTD date | High | Closed | GTD order placed but GTD date is displaying wrong |  |  |  | Done. But not properly tested, rasied concern to Angel team on mail. | Nikhil | 1.0.0.0 |  | 2019-04-16 | uTrade
76 | 14.03.2019 | MCX | FUTCOM | Order placement | System does display order type Market Expected Result : System should allow to place order with order type Limit, Market, SL-Limit, SL-Market | Client ID : A81827 Exchange : MCX Scrip : GOLD 19MAR FUT Validity : GTD Order Type : Market | 1) Log-in with Client ID 2) Select GOLD 19MAR FUT 3) Press F1/F2 on scrip 4 ) Select Validity = GTC 5) Select Order Type = Market | High | Open | This point is dependent on Point no. 77. Angel will check and revert, once we get release from OMNESYS. (04-Apr-2019) |  |  |  | 03 June Market & Sl added in MCX in 31st May release | Nikhil | 1.0.0.0 | done | Angel to revert | angel
77 | 14.03.2019 | MCX | FUTCOM | Order placement | SL-M order is getting rejected due to reason Bad Input 54205 Expected Result : System should allow to place SL-M order | Client ID : A81827 Exchange : MCX Scrip : GOLD 19MAR FUT Validity : GTD Order Type : SL-M Price = 0.00 Tr.Price = 31500 | 1) Log-in with Client ID 2) Select GOLD 19MAR FUT 3) Press F1/F2 on scrip 4 ) Select Validity = DAY 5) Select Order Type = SL-M | High | Open | 30/3/2019 Fucntionality is not available in current exe Market order and SL-Market should be available for MCX segment |  |  |  | 03 June Market & Sl added in MCX in 31st May release | Nikhil | 1.0.0.0 | done | Angel to revert | angel
78 | 18.03.2019 | All | All | Message Bar (AMX server down) | System does not display message in message AMX server disconnected | NA | 1) Log-in with Client ID 2) Place order when AMX server is down | High | Closed | In provide build in message bar it is displaying AMX- connected or disconnected |  |  |  | Need Discussion | Nikhil | 1.0.0.0 |  | Duplicate | uTrade
79 | 20.03.2019 | BSE | EQ | Log-in | Log-in in UAT_TCP system is having following error "Some symbol can't be updated correctly as market data tcp channel is not connected" Expected : System should log-in Successful without displaying any error | LoginID : A103403 Password : abc123 |  | Showstopper | Closed | Angel will check and revert (04-Apr-2019) |  |  |  | uTrade: - This comes when MCL is not running. A corner condition and important popup. As discussed with Priyank if any front-end to MCL system connectivity issue is resolved , this will not come. | Nikhil | 1.0.0.0 | Void | Angel to revert | Angel
80 | 20.03.2019 | All | All | Save/Load Work space from file | System does not allow to use .wps file created from tcp setup to udp setup System should allow to user work space .wps file in any set up e.g tcp, udp | Create market watch of multiple scrip | 1) Log-in with Client ID 2) Create market watch of multiple scrips 3) Go to configuration 4) Save work space to file 5) copy and paste .wps file in udp set up 6) Open .wps file from udp setup | Low | Open |  |  |  |  | Need to check, Will do if a bug. 03 June this is a behaviour the MW scrips are not added in worksp[ace instead in local DB | Nikhil | 1.0.0.0 | void | NA | angel
81 | 20.03.2019 | All | All | Order Placement | System is not allow to place order and not getting response from exe User is doing any activity no response found from exe (E.g order is getting in queue getting put order request received from NT) System should display validation message : "Session expired" or put order request received" | Place Load of multiple orders | 1) Log-in with Client ID 2) Place load of multiple orders 3) Place Order in BSE TCS from utrade | Showstopper | Open | As per discussion with sumit need to show this message as a notification. "Put order request received" Same is receiving from middleware need to be display in front end. 20/05/2019 Issue Still persist. Application is not display "Put Order Request Received" message. |  |  |  | As discussed, need to show this message as a notification. "Put order request received" 11 Apr: This has already been delivered in March-end release, rest of the problem needs to be resolved at Server level 03 June: Need clarity what exactly is pending at utrade | Nikhil | 1.0.0.0 | Done | Angel to revert | angel
82 | 20.03.2019 | All | All | Save/Load Work space from file | System does not allow to load Portfolio holding screen if it is saved in .wps file Expected Result : System should display all screens which are saved as work space | NA | 1) Log-in with Client ID 2) Close all other screen 3) Select Holding screen 4) Select Indices 5) Save work space as new1.wps 6) Go to default work space 7) Load Work space new1.wps | Medium | Open |  |  |  |  | 03 June This will be added in dock widget | Nikhil | 1.0.0.0 |  | June | uTrade
83 | 20.03.2019 | All | All | Order Book | System does not display validation message before cancel order Expected Result : System should display validation message : "Do you want to cancel Order?" | Client ID : A81827 Exchange : MCX Scrip : GOLD 19MAR FUT Validity : GTD Order Type : SL (Sell Order) Price = 32,000 Tr.Price = 31500 | 1) Log-in with Client ID 2) Open Order book 3) Select open order 4) Right Click and cancel | High | Closed |  |  |  |  | Done | Nikhil | 1.0.0.0 | Open | 2019-04-16 | uTrade
84 | 22.03.2019 | BSE | EQ | Order Placement | System does not allow to place order in M-Series stock based on lot size with disclosed Qty. Expected Result : System should calculate disclosed Qty based on lot (qty) for BSE , M-Series Stock | Client ID : A81827 Exchange : BSE Scrip : EFPL Series : M Qty : 20 Product Type = MARGIN | 1) Log-in with Client ID 2) Place order in BSE EQ 3) Select Product type = Margin | High | Closed |  |  |  |  | Discussion | Nikhil | 1.0.0.0 |  | Angel to revert | uTrade
85 | 22.03.2019 | All | All | Look-up Tree | Following drop down should be in Ascending Order: Look Up Tree > "Instrument" filter should be in alphabetical sequence | NA | 1) Log-in with Client ID 2) Open look up tree | Low | Open |  |  |  |  | will do | Nikhil | 1.0.0.0 | Open | Ph-2 | uTrade
86 | 25.03.2019 | All | All | Alert server | System does not display any mesage if Alert server is not working It allows to place order but does not display the same in any of order book Expected : System should display a alert message about alert server down | NA |  | Showstopper | Closed | 30/3/2019 As discussed with Sumit, Message does display for First login but it goes at bottom due all response received from System. So message should display at every some interval and Can we make it auto-reconnect if notifier is down and it get conneted in sometime? |  |  |  | uTrade: - We display this message in the bottom message bar whenever Alert notifier is connected/disconnected. As discussed with Priyank, it is working fine. This message is also needed in the case of first login if Alert Notifier is down. | Prayank | 1.0.0.0 | Done | March-end | Angel
87 | 30.03.2019 | CDS | OPTCUR | Order Book | System is displaying two records same cancelled order in rejection history report . | Scrip : JPYINR 19MAR63PE Order type : SL Limit Price = 0.4775 Trig. price = 0.4800 Mode : Sell | 1) Log-in with Client ID 2) Cancel Open Order 2) Go to Rejection History report 3) Verify rejected orders | High | Deferred |  |  |  |  | Duplicate. Rasied earlier as well. Already pending at Omneysis. | Prayank | 1.0.0.0 |  | At Angel | Angel
88 | 30.03.2019 | CDS | NSE/BSE EQ | Market Picture | System does not display following details in Market picture: 1) 52W High / 52W Low 2) LUT | Scrip: HDFC | 1) Log-in with Client ID 2) Select scrip form market watch 3) Right click and open market picture | High | Open | LUT is not getting updated |  |  |  | 52 w High, Low is done. Not tested for all exchanges as data was not received form Angel API, communicated to Angel team. LUT is still pending, checking with Exchange if they provide us the data. Must be handled in next delivery. 03 june: LUT will be added. | Nikhil | 1.0.0.0 |  | June | uTrade
89 | 30.03.2019 | All | All | Charts | Charts functionality is not working Expected : System should display on selected scrip Chart from Marketwatch by clicking on Charts | Scrip: ONGC | 1) Log-in with Client ID 2) add scrip ONGC in Marketwatch 3) Click on Charts on main header | Showstopper | Deferred | [5 empty] | Prayank | 1.0.0.0 | done |  | angel
90 | 30.03.2019 | All | All | Log-in | 1) System allow to login utrade application without password policy validation if password changed from nest trader and with same client id login to nest trader. Expected Result: System should ask for change password from utrade application if password policy conditions are not met | Scrip : USDINR 19MAR73PE | Steps to recreate: 1) Select Client Code A81827 2) Change password from nest trader Admin (abc123) 3) Login to Nest trader client and change password to (abc321) 4) Login/Logout from Client Nest trader 5) Login to utrade application with a password (abc321) | Showstopper | Closed | 9/4/2019 Front end issue 09/04/2019 As discussed today with Sumit, utrade will fixed this issue in 12th Aprl release. As discussed, once Issue No. 92 is fixed, issue No. 90 will be solved |  |  |  | Password validation is corrected as requested which is mixed case is not mandatory now. | Nikhil | 1.0.0.0 |  | 2019-04-16 | uTrade
91 | 30.03.2019 | All | All | Net Position | System is not displaying proper alignment in net position at bottom Total and All calculation to it respective column Expected result: System should displaying proper alignment in net position the bottom Total and All calculation to it respective column |  | Steps to Create 1) Create position for All segments 2) Verify the alignment of Bottom total and All calculation of respective column | Medium | Open |  |  |  |  | 03 June Will be done | Prayank | 1.0.0.0 |  | June | uTrade
92 | 30.03.2019 | All | All | Password Policy | System does not accept the change password as all character in small case Expected: System should accept passowrd policy as per JIRA story 414 Where it is return Password should Alpha and numeric Special character is optional |  | 1. Log-in utrade Application 2. Log-in with A81827 3. Change password from Configuration>ChangePassword | High | Closed |  |  |  |  | Password validation is corrected as requested which is mixed case is not mandatory now. | Prayank | 1.0.0.0 |  | 2019-04-16 | uTrade
93 | 30.03.2019 | All | All | Holding | System does not display proper holding qty and collateral qty.i.e.It display total qty as 300 in HDFC Expected : System should display proper holding qty in Holding .i.e should display 400 as total qty in HDFC |  | 1) Update following of HDFC 1) 100 qty in NSE from holding 2) 100 qty in BSE from T1- holding 3) 200 qty in BSE from holding | Showstopper | Open | 9/4/2019 In API it is calculating proper but in Front it is not displaying the same |  |  |  | Could be at Angel-end. "Discussion was done with Priyank about Holding flow understanding, this is still pending. Let's discuss to close isin vs Series gap." | Prayank | 1.0.0.0 |  | Angel to revert | Angel
94 | 30.03.2019 | All | All | Funds View | System is not displaying proper value in Limit Utilization of view. It is displaying as 0 Expected : System should display proper value in Limit Utilization of Fund view.When stock sold from DP or when i buy today a new position |  | 1) Update Limit from Admin as follows 1) Cash Deposit - 25000 2) Adhoc Deposit - 100 3) Notional Deposit - 100 4) Misc Deposit -100 5) Collateral 500000 ( by adding ICICI bank holding from holding of 500qty of Rs 100) | Showstopper | Open | 9/4/2019 In API we are calculating the Limit utilization but in front end it is not displaying 10/4/2019 As discussed with sumit, uTrade will check and confirm 06/06/2019 Scenario already explained to vikas on call on 27/5/2019 |  |  |  | Could be at Angel-end. 11 Apr Vikas & Priyank are checking. | Prayank | 1.0.0.0 |  | At Angel | Angel
95 | 30.03.2019 | All | All | Login | By Default Client dropdown option should be selected on the Login window |  | 1. Double Click on muTrade_Client.exe | Low | Closed |  |  |  |  | Done | Suraj | 1.0.0.0 |  | 2019-04-16 | uTrade
96 | 30.03.2019 | All | All | Configuration Setting | Required clerification on the configuration setting's options |  | 1. Double Click on muTrade_Client.exe 2. click on setting icon | High | Closed | Need to discussed with uTrade team 06/06/2019 Clairification given to suraj by vikas |  |  |  | Need Discussion. Awaiting con call from Angel team. | Suraj | 1.0.0.0 | done | 2019-04-16 | angel
97 | 30.03.2019 | All | All | Login | User Blocked message should be displayed if the user attempted invalid login details at the 3rd time | Login Id- ABL152 Password - abc321 | 1. Double Click on muTrade_Client.exe 2. Type valid login id & invalid password click on Login button (try to login thrice with invalid password) | High | Closed |  |  |  |  | Could be at Angel-end. | Suraj | 1.0.0.0 |  | Angel to revert | Angel
98 | 30.03.2019 | All | All | Forgot Password | Fields can't be empty messaged displayed if all fields are blanked & clicked on sumbit button Expected : System should displayed Field name if there is any fields empty while forgot password |  | 1. Double Click on muTrade_Client.exe 2. Click on Forgot password icon 3. Click on send button | High | Closed |  |  |  |  | Done | Suraj | 1.0.0.0 |  | 2019-04-16 | uTrade
99 | 30.03.2019 | All | All | Forgot Password | Mobile No field lenght should be of 10 digit | Login Id - ABL152 Email Id -abc@gmail.com Pan No - abcde1234z Mobile No - 98765463261 | 1. Double Click on muTrade_Client.exe 2. Click on Forgot password icon 3. Type Login Id, email id, Pan no & invalid mobile no 4. Click on send button | Medium | Closed |  |  |  |  | Done | Suraj | 1.0.0.0 |  | 2019-04-16 | uTrade
100 | 30.03.2019 | NSE / BSE | Equity | Holding | System is display NSECM as default segment in dropdown while selling stock from Holding Expected: System should allow to select any of Exchange NSECM and BSECM while selling stock from Holding |  | 1) update holding from admin in NSECM or BSECM | Showstopper | Closed | 9/4/2019 Front end issue |  |  |  | We have this feature of opening Holding sell form for the exchange where maximum Bid is found (for same isin). Now, change of Market option is enabled so that user has the choice to sell this at any other market as well. But this could not be tested because we were not able to add holdings from NEST, issue rasied separately to Angel team. 03 June: This is already done. Please check | Prayank | 1.0.0.0 |  | 2019-04-16 | angel
101 | 30.03.2019 | NSE FO/MCX | Derivative | Net position | System is displaying 0 in All field in Net position for previous day positions Expected : System should proper data in all fields in Net position for previous day position. |  | 1) Upload previous day position in NSE FO and MCX segment 2) Verify the same in Net position | Showstopper | Closed | 9/4/2019 Front end issue |  |  |  | Could be at Angel-end. Need Discussion | Prayank | 1.0.0.0 |  | Angel to revert | Angel
102 | 30.03.2019 | NSE FO/MCX | Derivative | Net position | System is displaying previous day position in Day and ALL both. Expected : System should display previous day position in ALL and Todays position in Day |  |  | Showstopper | Open | 9/4/2019 Front end issue 06/06/2019 Will provide clarification |  |  |  | Could be at Angel-end. Need Discussion | Prayank | 1.0.0.0 |  | Angel to revert | Angel
103 | 30.03.2019 | NSE EQ | Equity | Order Book | System is not displaying the Exchange order for confirmed order in order book Expected : System should display the exchange order number in order book for confirmed order |  | 1) Place a sell order in TATAMOTORS at price 182 Rs of 10 qty 2) verify the same order in order book | Showstopper | Closed | Need to discuss 10/4/2019 uTrade will check and confirm Issue screen shot provided in separate mail. Issue Still persist, refer screen shot No. 103 in "Screen Shot" sheet. |  |  |  | 11 April: uTrade is not receiving Exchange Order Id in Open Order API as discussed with Kalpesh, Vivek. | Prayank | 1.0.0.0 |  | Angel to revert | Angel
104 | 30.03.2019 | All | All | Login | System is not getting login if update scrip details is canceled while updating Expected : System should cancel update of scrip details and not login of application |  | Steps 1) click on exe 2) Insert the Login credentials 3) Check the update Scrips 4) Now click on login 5) On start of scrip downloading cancel the downloading by clicking on cancel or by esc from keyboard. | Showstopper | Closed | 9/4/2019 Front end issue |  |  |  | As discussed, this is by design and not an issue. | Prayank | 1.0.0.0 |  | Void | uTrade
105 | 30.03.2019 | All | All | Login / Session Expired | System is not displaying session expiry message while cancelling the order 2nd time from order report Expected : System should displayed session expiry message every time whenever cancel the order | Userid : ABL155 Password : abc123 | 1) Login in utrade, Place a Buy Order in ACC at price 1400 of 5 qty (Order should be Pending) 2) Login in other application with the same client 3) Again go to utrade -> Order report -> try to cancel placed order twice. 4) At the second time system is not displaying session expiry message | Showstopper | Open | 9/4/2019 It is working fine while placing order and then it should display expiry message in cancelation also. 10/4/2019 As discussed with sumit, uTrade will check and confirm |  |  |  | At Angel-end. This is happening due to Connection-less architecture. 11 April. As discussed with Kapesh, We are sending the request but may be the Lib is not sending the request to Back-end. | Suraj | 1.0.0.0 |  | Angel to revert | Angel
106 | 20.03.2019 | All | All | Configuration | Lock workstation timer setting is not working on real time base Expected : System Lock workstation time on real time and not after re-login | NA | 1) Go to Configuration Setting 2)Check the check box Lock Workstation Timer 3) verify the same on real time | High | Closed |  |  |  |  | Done | Prayank | 1.0.0.0 |  | 2019-04-16 | uTrade
107 | 20.03.2019 | All | All | Order Placement | System display " Data updation is running.Please wait" while placing order and does not download all orders and messages in front end after successful login Expected : System should not display any error message and should download all order and messages on successful login. |  |  | Showstopper | Closed | 9/4/2019 This issue was simulated to utrade and next day again same issue occur so reported the same |  |  |  | This comes at the time of login + order updates coming, very rare corner scenario. Please help in reproducing the issue, if frequent. | Prayank | 1.0.0.0 |  | Angel to revert | uTrade
108 | 2019-02-04 | All | All | Net Position | System is allowing to place BE symbol's square off order from the net positions Expected : System should not allowed to place BE symbol's square off order from the net positions | Scrip: ANTGRAPHIC | 1) Log-in with Client ID 2) add scrip ANTGRAPHIC in Marketwatch 3) Create a buy Position 4) Square off the same from net position. | Showstopper | Open | 9/4/2019 Need to handle at frond end |  |  |  | Should be handled at BE. | Suraj | 1.0.0.0 |  | At Angel | Angel
109 | 2019-02-04 | All | All | Holding | System is not allowing to place sell order of BE series scrip from Holdings & displaying following error Error : RMS:Rule: Check T1 holdings including TT/BE/Z/T/TS ,No Holdings Present for entity account-ABL152 across exchange across segment across product Expected System should allow to place sell order of BE series scrip from holding | Scrip: ANTGRAPHIC | 1) Log-in with Client ID 2) add ANTGRAPHIC positions in Holdings from admin 3) Place sell order from holdings | Showstopper | Closed | 9/4/2019 Not an issue |  |  |  | As discussed with Vivek, this is void | Suraj | 1.0.0.0 |  | Void | uTrade
110 | 2019-04-04 | All | All | Net Position | System is not updating Net position on real time on every trade and it should also update even after uploading the previous day position Expected : System should update Net position on real time on every trade and with previous day positions |  | 1) update previous day positions from admin 2) Create new position and verify the same in net position | Showstopper | Closed | 9/4/2019 As discussed with uTrade (Vikas), Net position is not getting updated on real time basis. Simulation is given for the same. |  |  |  | This is not a Front-end issue. Whenever there is load on Angel middleware , the responses through alert notifier are received very slowly , due to which updation delay is observed. | Prayank | 1.0.0.0 |  | At Angel | Angel
111 | 20.04.2019 | All | All | Order form setting | 1) System is displaying alert message for "On the Limit scenarios" for order qty, Should allow placing order without the alert message: Actual Result: System is displaying Alert message: "Order Qty Exceed the configured Alert Value" |  | I) Example: Order Qty Alert Set = 2 Place Order: Exchange Segment = BSE Scrip TCS = Order Qty = 2 Validity = DAY Product Type = MIS Price = 2000 | High | Open |  |  |  |  | 03 June As per discusion, amendment is needed in the display message. Will be done | Nikhil | 1.0.0.0 |  | June | uTrade
112 | 20.04.2019 | All | All | Order form setting | 1) System is displaying alert message for "On the Limit scenarios" for "Price alert % , Should allow placing order without the alert message: Actual Result: System is displaying Alert message: "Price alert % Exceed the configured Alert Value" |  | II) Example : Price Alert% Set = 100 Place Order : Exchange Segment = BSE Scrip TCS = Order Qty = 2 Validity = DAY Product Type = MIS Price = 2000 | High | Open |  |  |  |  | 03 June As per discusion, amendment is needed in the display message. Will be done | Nikhil | 1.0.0.0 |  | June | uTrade
113 | 20.04.2019 | All | All | Order form setting | 1) System is displaying alert message for "On the Limit scenarios" for Order Value Alert, Should allow placing order without the alert message: Actual Result: System is displaying Alert message: " Order Value Exceed the configured Alert Value" |  | III) Example : Order Value Alert Set = (Price * Qty) = 2000*1 = 2000 Place Order : Exchange Segment = BSE Scrip TCS Order Qty = 1 Validity = EOS Product Type = MIS | High | Open |  |  |  |  | 03 June As per discusion, amendment is needed in the display message. Will be done | Nikhil | 1.0.0.0 |  | June | uTrade
114 | 20.04.2019 | All | All | Session Expiry | A session is getting expired frequently after 5 min of idle time. |  |  | High | Open |  |  |  |  | 03 June Angel to provide clarity | Nikhil | 1.0.0.0 |  |  | angel
115 | 22.04.2019 | All | All | Market Picture | System is not displaying any information until tick received for Broadcast in market picture. |  |  | High | Open | utrade they will provide solution for same. 24/04/2019 |  | Please help show this to our QA team. 22/04/2019 |  | 03 June Will be done, Need Angel team help as well for investigation. Some corner scenario. | Prayank | 1.0.0.0 |  | TBD | uTrade
116 | 22.04.2019 | All | All | Login | System went in no response mode when load is generated OR when there is late response from server |  |  | Showstopper | Deferred | In Connected arhitecture issue will get resolved. 24/04/2019 |  | As discussed earlier as well, this is Angel middle-layer issue 22/04/2019 |  |  | Prayank | 1.0.0.0 | done |  | angel
117 | 22.04.2019 | All | All | Order placement | System does not display any response messages in message bar on self trade. |  |  | Showstopper | Closed | utrade they will provide solution for same. 24/04/2019 |  | Please explain & show this to QA team 22/04/2019 |  |  | Prayank | 1.0.0.0 |  |  | uTrade
118 | 22.04.2019 | All | All | Market Picture | Systems does not allow to open Market picture window even if order entry form window is open |  |  | High | Open | utrade they will provide solution for same 24/04/2019 |  | uTrade Will check & confirm 22/04/2019 |  |  | Prayank | 1.0.0.0 | Done |  | angel
119 | 22.04.2019 | All | All | Login | System is not displaying any message when AMX server is down or Alert notifier is down It get hang by displaying "Requesting Login" |  |  | Showstopper | Deferred | In Connected arhitecture issue will get resolved. 24/04/2019 |  | As discussed earlier as well, this is due to connection less architecture. 22/04/2019 |  |  | Prayank | 1.0.0.0 | done |  | angel
120 | 22.04.2019 | All | All | Order placement | Systems is not displaying proper date in order book after placing GTD order with date mention. |  |  | Showstopper | Open | utrade will provide solution for same 24/04/2019 |  | We could't test GTD end-to-end due to some issues at Angel-end, as mentioned in the sheet as well. Please check with Kalpesh once, must he at API end. 22/04/2019 |  | 03 June More details needed, what exaclty is the issue pending at uTrade end. | Prayank | 1.0.0.0 |  |  | angel
121 | 22.04.2019 | All | All | Login | Broadcast is not working when 2 client exe is login with different user. |  |  | Showstopper | Open | Simulation provided, utrade will provide solution for same 24/04/2019 |  | Need details & please show this to our QA team. 22/04/2019 |  | 03 June utrade to check again with Prayank | Prayank | 1.0.0.0 |  | June | uTrade
122 | 22.04.2019 | All | All | Market Picture | Sometime Client exe get crash on F6 it is not getting simulated everytime but it occurs in between today 3 times got crash |  |  | Showstopper | Closed | utrade they will provide solution for same 24/04/2019 |  | Help recreate this & show to our QA team. 22/04/2019 |  |  | Prayank | 1.0.0.0 |  |  | uTrade
123 | 03.05.2019 | All | All | Change Password | System allow to change password with only numerical value (E.g 123456) Expected Result : System should only accept alphanumeric password | newpassword = 123456 | 1) Go to Configuration Setting 2) Click on Change password 3) Enter Old password 4) Enter new password 5) Confirm new password | High | Open |  |  |  |  | 03 June Will be done | Nikhil | 1.0.0.0 |  | June | uTrade
124 | 03.05.2019 | All | All | Market Watch | Market watch : 1) "Add all" Button is disabled for adding equity segment other series (BE,EQ,BL etc) it was working earlier 2) Avg Ask price and Avg Bid price is displaying "0" value 3) Total Traded Quantity field is blank 4) BpsLevel shows 0 5) Trade Unit,price unit, quantity unit, delivery unit is blank |  | 1) Go to market watch | High | Open |  |  |  |  | 03 June. Add all button is removed to avoid bandwidth issues, where if a client accidentally add all the derivative instruments. This was more relevant for algo clients hence made hidden in recent version. Will check for other points in this issue. | Nikhil | 1.0.0.0 |  | TBD | uTrade
125 | 03.05.2019 | All | All | Symbol information | 1) Symbol Information following details are not getting a) TFT Status b) Issued capital |  | 1) Go to market watch 2) Select scrip 3) Right Click and 4) Select Symbol Information | High | Open |  |  |  |  | 03 June Data is not received in Ange l API | Nikhil | 1.0.0.0 |  | TBD | uTrade
126 | 03.05.2019 | All | All | Market Picture | Market Picture : Web Rest Feeds: Last update time is not getting in utrade client exe , LUT field (Not getting Last update time) |  | 1) Go to Books 2) Select Market picture | High | Open | [5 empty] | Nikhil | 1.0.0.0 | duplicate |  | angel
127 | 07.05.2019 |  |  | Default Market Watch | Scrip added in market watch of client A are seen in other login too. |  | Login with client A (say ABL152)>>Add few scrips in default market watch>>Logout>>Login with client B (say ABL180)>>Check default market watch | High | Open |  |  |  |  | 03 June As discussed, client id will also be added in the key, hence a scrip added in MW of one client will not display in another ( if logged in throgh same machine/folder) | Jalak | 1.0.0.0 |  | June | uTrade
128 | 07.05.2019 |  |  | Market Watch | Unable to change window size once increased |  | Close order depth window and drag market watch window up, then try to drag it down | Low | Open |  |  |  |  | MW is not being moved from top to bottom if scrip are deleted form MW. | Jalak | 1.0.0.0 |  | Ph-2 | uTrade
129 | 07.05.2019 |  |  | Market Watch | No option to delete/remove added market watchlist |  | Add a market watchlist from orders. Once added, try to delete/remove it. | High | Open |  |  |  |  | 03 June Will be done. | Jalak | 1.0.0.0 |  | June | uTrade
130 | 07.05.2019 |  |  | Broadcast | Change and Change% columns is showing 0.00 once the market hours are closed. |  | Add any stock. Check columns "Change" & "Change %" of broadcast after market hours | High | Open |  |  |  |  | 03 June Will be done. | Jalak | 1.0.0.0 |  | June | uTrade
131 | 07.05.2019 | All | All | Funds View | Funds View observations: 1) "Fund transferred today " updated from API is not getting included in total available cash 2) Fund withdrawal/allocation is not getting reflected in client exe 3) Collateral, Credit for sale, option CFS not available 4) Unrealized MtoM is not considered as MTM profit/Loss in client exe 5) Realized MtoM is not considered for Booked PnL 6) Fund utilization total is directly consider value of "Margin used" total of fund utilized is mismatched with margin used 7) Fund available for trading is mis-match with Nest trader RMS cash credit screen |  | 1) Go to Books 2) Verify Fund view after PayIN/Pay out 3) Use fund transfer API | Showstopper | Open |  |  |  |  | 03 June Angel to provide clarity | Nikhil | 1.0.0.0 |  |  | angel
132 | 08.05.2019 |  |  | Message Bar | Application is not displaying pending order alert in message bar |  |  | High | Open |  |  |  |  | Order displaying in OB is not displaying in Message bar. Pending & exchange order id. And all orders as well. 03 June All orders will be added in message bar | Nikhil | 1.0.0.0 |  | June | uTrade
133 | 08.05.2019 |  |  | Order Book | uTrade is not displaying "open pending" orders in Order Book |  |  | High | Open |  |  |  |  | We receive from Angel, should show in OB as well. 03 June Pending & other orders will be shown in OB | Nikhil | 1.0.0.0 |  | June | uTrade
134 | 08.05.2019 |  |  | Order Book | Application is not displaying all orders in order book, e.g. Pending order, Rejected order, canceled orders etc. |  |  | High | Open |  |  |  |  | Need all statuses in OB as well and rejection, TB should also show. 03 June Pending & other orders will be shown in OB. And will be pushed to tradebook & Rejection history as well like existing implementation | Vivek | 1.0.0.0 |  | June | uTrade
135 | 08.05.2019 |  |  | Order Book | Orders are not display in order book, if alert notifier is not connected |  |  | High | Open |  |  |  |  | alert notifier auto reconnect. Alert notifier, is auto reconnecting, but the missed orders should be shown. 03 June Need discussion b/w Sahil & Kalpesh | Vivek | 1.0.0.0 |  | TBD | uTrade
136 | 08.05.2019 |  |  | Alert Notifier | Alert notifier is not connected automatically, if alert notifier is down |  |  | High | Open |  |  |  |  | 03 June Will be done. | Vivek | 1.0.0.0 |  | June | uTrade
137 | 09.05.2019 | All | All | Order placement | System is not displaying following message while placing order in Intraday product type "All intraday positions are squared off before the end of day’s session. In case of MTM loss above 80 % of the margin all your open positions including other order type will be liquidated." Expected : System should display the above mention messsage on intraday product type order placement. |  |  | Medium | Open |  |  |  |  | 03 June: not at uTrade end. If needed angel to provide the message, then only we can show. | Nikhil | 1.0.0.0 |  | NA | angel
138 | - | - | - | Order Flow | Exchange Order Id is received as empty in Open order response through Alert Notifier. |  |  | High | Open |  |  |  |  | 03 June Will check & do | Vivek | 1.0.0.0 |  | June | uTrade
139 | - | - | - | Position Conversion | Garbage TradeReport is being received through Alert Notifier after Position Conversion. |  |  | High | Open |  |  |  |  | 03 June Will check & do | Vivek | 1.0.0.0 |  | June | uTrade
140 | - | - | - | API Connection-less Architecture | Angel API Connection-less Architecture resulting in not able to identify Sever (Order Flow) disconnection. |  |  | High | Open | [5 empty] | Vivek | 1.0.0.0 | done |  | angel
141 | - | - | - | 2FA Password | This is a web based API, you guys would be implementing C/C++ API for 2FA soon? We have not yet used any of the WEB API in this Project. |  |  | High | Open |  |  |  |  | 03 June need discussion on using web API from Desktop exe | Vivek | 1.0.0.0 |  | TBD | uTrade
142 | 08.05.2019 | All | All | Net Position | System is not display Net value proper for only Sell position in Net Position Expected : System should display Net value proper for only sell order in Net Position i.e. it should display negative value in net position |  | 1) create a sell position for client 2) Verify the Net value in Net position | High | Open |  |  |  |  | 03 June. Will check & revert Omny, odin show negative values. QA team will check with other s/ws. | Nikhil | 1.0.0.0 |  | TBD | uTrade
143 | 08.05.2019 | All | All | Order Entry | System is display wrong qty in order entry form of BSECM segment Expected : System should display proper qty in order enrty form for BSECM segment |  | 1) Open order form select NSEFO segment select ONGC symbol 2) Keep the Order Form window open select BSECM segment and type symbol ONGC 3) Verify the qty after selecting symbol | High | Open |  |  |  |  | 03 June Done 7 delivered in 31st May release. | Prayank | 1.0.0.0 | done |  | angel
144 | 15.05.2019 | All | All | Order Placement | "Product type" gets disabled and "Fill account detail" error msg is seen when user tries to place an order in disabled exchange. Expected: Product type should be seen and if it is not available then msg shoudl be "Product type is not available" | Client: A81827 Exchange disabled: CDS Screenshot in sheet 2 | 1. Disable an exchange, say CDS, for a user from NEST Trader. 2. Login with that user and try to place order in the disabled exchange | Medium | Open |  |  |  |  | 03 June Will be done if a proper bug | Jalak | 1.0.0.0 |  | June | uTrade
145 | 15.05.2019 | All | All | Order Placement | Symbol disappears when "Enter Key" is used instead of TAB key during order placement. Expected: Searched scheme should stay when Enter key is used | NSECM: YESBANK Screenshot in sheet 2 | 1. Open order placement window 2. Search any symbol and press enter to select the symbol | Medium | Open |  |  |  |  | 03 June Will be done if a proper bug | Jalak | 1.0.0.0 |  | June | uTrade
146 | 17.05.2019 | All | All | Master download | After relogin System is not downloading the master of all segment on real time enabling the segments Expected :After relogin System should download all masters of enabled segment on real time |  | 1) Before starting utrade exe on fresh day 2) Disable few segment for client 3) Login the client from utrade 4) Verify the master for disabled segment 5) System will not display 6) Now enable all segment for same client 7) Relogin the client 8) Verify the master of all for same client in utrade.exe | Showstopper | Open |  |  |  |  | 03 June If Update scrip master checkbox is checked complete scrip master is downloaded at every login/re-login. We have a setting in whera a user can shose the default behaviour of this checkbox (checked / unchecked) form configuration settings. | Prayank | 1.0.0.0 |  |  | angel
147 | 29.05.2019 | All | All | Configuration Setting>> General setting | System is not display proper qty as per the segment selected in order entry window Expected : System should display proper qty as per the segment selected in order entry window |  | Step 1: Configuration Setting>> General setting >> Uncheck use quantity in lots Step 2: Open order entry for MCX segment symbol GOLDM Step 3 : Now click up arrow key Step 4 : Verify the qty in order entry window | Medium | Open | [5 empty] | Prayank | 1.0.0.0 |  |  | uTrade
148 | 2019-06-06 | All | Equity | Combined Order Depth | Systems is displaying an error of "Corresponding symbol not found" while verifying the order depth window for symbol available only in one segment. Expected : System should open combined order depth window if symbol is available in any of one segment of equity |  | Step 1 : Add scrip CDSL in Marketwatch Step 2 : Select the scrip and right click on it select Combined market depth Step 3 : Verify the same | Showstopper | Open |  | We have intentionally implemented it in this way to not show blank half side. I would still suggest to not do in this way instead we can show normal order depth in this case (where one of the scrip is not available). Let's discuss & decide. |  |  |  | Suraj | 1.0.0.0 |  |  | uTrade
149 | 2019-06-06 | All | Derivatives/Currency | Multi Leg order window | System is not closing the mulit leg order window on clicking on ESC key Expected : System should close the mulit leg order window on clicking on ESC key |  | Step 1: Open Multileg Order Window Step 2: Press ESC key | Medium | Open |  | We will resolve it |  |  |  | Suraj | 1.0.0.0 |  |  | uTrade
150 | 2019-06-06 | All | Derivatives/Currency | Multi Leg order | Unable to place spread order, System displayed "Spread Orders are not supported" message Expected : System should allowed placed Spread Order | Market - NSEFO Order Category - SP Validity - Day Order Mode - Buy Instrument - Spread Symbol - Banknifty Expiry - 27Jun1927Jun19 Qty (Lot) - 1 Price = 0 | Step 1: Open Multileg Order Window Step 2: Type Order Details Step 3: Click on Place Order button | Showstopper | Open |  | As communicated earlier & through release notes as well. Spread order is not implemented, tested in this version due to some issue at Angel API end. |  |  |  | Suraj | 1.0.0.0 |  |  | uTrade
151 | 2019-06-06 | All | All | Charts | Chart is not working in UAT build Expected : System should plot chart as per symbols | Market - NSE Symbol - ACC | Step 1: Add symbol in the market watch Step 2: Select symbol & select chart option | Showstopper | Open | [5 empty] | Suraj | 1.0.0.0 |  |  | uTrade
152 | 31/05/2019 | All | All | Login>> Scrip Master download | System is not downloading the master and not getting logged in sucessfully Expected : System should download the masters and should get logged in sucessfully |  |  | Showstopper | Open | [5 empty] | Vivek | 1.0.0.0 |  |  | uTrade
153 | 2019-11-06 | All | All | Market picture | For TCP & UDP in all segments, 52W High & Low is not seen in Market picture for many scrips. e.g. Screenshot attached (Client: K71501) Expected: 52W high & low should be seen | NSEFO: Future Scrip: SUZLON | 1. Select SUZLON scrip of NSEFO future 2. Open Market picture 3. Check 52W high & low | High | Open | [5 empty] | Jalak | 1.0.0.0 |  |  | uTrade
154 | 2019-11-06 | NSE | Equity | Market picture | For TCP & UDP, 52W high/low does not change immediately if the price goes beyond previous day's recorded 52W high/low. Issue observed for NSECM but can be present for all segments Expected: 52W high/low should change immediately if price goes beyond last recorded data | NSECM: RELCAPITAL | 1. Select RELCAPITAL scrip of NSECM 2. Open Market picture 3. Check 52W high & low | Medium | Open | [5 empty] | Jalak | 1.0.0.0 |  |  | uTrade
155 | 2019-11-06 | BSE | Equity | Market picture/ Best five | For BSECM, No.of orders is seen as 0 for all scrips. Same is working in speedpro Expected: No. of orders should be seen for all scrips | BSECM all scrips | 1. Select any scrip of BSECM 2. Open market picture or best five 3. Check no.of orders column | Showstopper | Open | [5 empty] | Jalak | 1.0.0.0 |  |  | uTrade
156 | 2019-11-06 | All | All | Market watch | Static broadcast is seen in UDP build for all scrips & exchanges. Expected: Broadcast should be dynamic | Live UDP build | 1. Open Live UDP build 2. Add scrips of multiple segments 3. Check broadcast | Showstopper | Open | [5 empty] | Jalak | 1.0.0.0 |  |  | uTrade
157 | 2019-11-06 | NSE | Equity | Market watch | For NSECM, Change and Change(%) turns 0.00 after market hours. Same is working in speedpro Expected: Verify last broadcast after market hours | NSECM all scrips | 1. Select any scrip of NSECM in which trading has been active during market hours. 2. Check columns "Change" and "Change(%)" after market hours | High | Open | [5 empty] | Jalak | 1.0.0.0 |  |  | uTrade
158 | 2019-07-06 | NSE FO/MCX | All | Broadcast | System is not displaying broadcast for any of the scrip in NSE FO and MCX segment Expected : System should display broadcast for any scrip in NSE FO and MCX segment |  |  | Showstopper | Open | [5 empty] | Prayank | 1.0.0.0 |  |  | uTrade
159 | 19-6-2019 | NSE/BSE | EQ | Holdings | System does not update sold qty in holdings Following values are not getting 1) Close Price 2) Invested Value |  | 1) Upload Holdings from Admin 2) Place sell order from holding 3) Trade Sell order | High | Open | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade
160 | 19-6-2019 | All | All | Funds View | MtoM profit/loss is not getting updated real time in Fund view |  | 1) Login to utrade 2) Verify MtoM Profit/loss from net position and fund view | High | Open | [5 empty] | Nikhil | 1.0.0.0 |  |  | uTrade

## Screen Shot (hidden)
| Issue No 56 | System should immediatly trade or cancel IOC order should not remain open in order book
| Issue No 56 |  | GTD,GTC,EOS order validity is not available
| Issue No 57 | Market order type is not available
| issue 58 |  | Getting rejection error Bad input for SL-M order placement
| Issue No 59 |  | System should display "Is Triggered" as No for stoploss sell order
| Issue No 60 |  | Holding value is not getting displayed
| Issue No 62 |  | System should display strike price in Ascending form
Issue No 63
Date : 20-March-2019
16
103 | System is not displaying the Exchange order for confirmed order in order book Expected : System should display the exchange order number in order book for confirmed order
127 | Mis match in Fund view and cash credit screen
128 | Net value (day) display positive value even if there is sell position.
Net value (day) display positive value even if there is sell position.
129
130
143
144
145
146

## Req. move to P 2 from P 1
Sr. No. | Feature | Phase - uTrade | Functionaities Covers | utrade Remarks
1 | My Portfolio | 1 | Done | Some issues pending at Angel's end
2 | Funds View | 1 | Done
3 | Charts | 1 | Done | Existing Intraday charting is delivered.
4 | Tick Watch | 1 | Done | Market watch
5 | Security Info | 1 | Done
6 | Web links | 1 | No | Pending at uTrade's end
7 | App Version | 1 | Done
8 | Multiple Work profiles | 1 | Done
9 | And Set Default WrkSpace | 1 | Done
10 | Same Order Window for Normal order and Bracket order | 1 | No | Deferred to Phase-2 | Phase2
11 | Order Book Filters according to status | 1 | Done
12 | Tabular Views with popout | 1 | Done |  | Done
13 | Order from charts | 1 | No | To be done with 3rd party library (ChartIQ or any other) | June
14 | Linking of Advanced charts | 1 | No | To be done with 3rd party library (ChartIQ or any other) | TBD
15 | MultiLeg Order including Spread | 1 | No | Deferred to Phase-2 | Angel
16 | Combined Best Five | 2 | No | Deferred to Phase-2 | Angel
17 | Top Gainers/Losers | 2 | No | Deferred to Phase-2 | July
18 | Margin Calculator on Order Form | 2 | No | Deferred to Phase-2 | July
19 | Login Module | 1 | Done
20 | Forgot Password | 1 | Done
21 | 2FA Password | 1 | No | Pending at Angel's end
22 | Change Password | 1 | Done
23 | Order Book | 1 | Done
24 | Trade Book | 1 | Done
25 | Net Position | 1 | Done
26 | Position Conversation | 1 | Done | Some issues pending at Angel's end
27 | Basic Scrip master - Download | 1 | Done

## Phase 2 Req.
Sr. No. | Jira Stories | Summary | Phase - uTrade | Jira Description | BRS | API / Lib | Remarks | uTrade | Efforts
1 | AMXTECH-71 | ChartsIQ Analysis | 2 | Yes | Yes | NA |  | Done
2 | AMXTECH-73 | Advance tick Watch | 2 | Yes | Yes | NA
3 | AMXTECH-74 | Advance Filter Watch | 2 | Yes | Yes | NA |  |  | 15
4 | AMXTECH-76 | MultiLeg Order | 2 | Yes | Yes | Yes |  | Done
5 | AMXTECH-78 | Compatibility Check | 2 | No | Yes | NA |  |  | 5
6 | AMXTECH-82 | Order from charts | 2 | No | No | NA |  |  | 15
7 | AMXTECH-83 | Order Window showing various values | 2 | No | No | NA |  |  | 8
8 | AMXTECH-84 | Same Order Window for Normal order and Bracket order | 2 | No | No | NA |  |  | 10
9 | AMXTECH-86 | Linking of Advanced charts | 2 | No | No | NA |  |  | 5
10 | AMXTECH-87 | Best quote Ladder | 2 | No | No | NA | Need to form through BCast |  | 5
11 | AMXTECH-103 | Combined Best Five | 2 | Yes | Yes | NA | Need to form through BCast | Done
12 | AMXTECH-104 | Top Gainers/Losers | 2 | Yes | Yes | Yes |  |  | 10
13 | AMXTECH-543 | Menus | 2 | No | No | NA | - |  | -
14 | AMXTECH-544 | Sidebar | 2 | No | No | NA | - |  | -
15 | AMXTECH-545 | Daily/ Research Reports | 2 | No | No | NA |  | 3rd Party | 10
16 | AMXTECH-546 | Alerts & Condition Generator | 2 | Yes | Yes | NA | Need to form through BCast |  | 30
17 | AMXTECH-547 | Online Backup and Auto Backup | 2 | Yes | Yes | NA |  |  | 8
18 | AMXTECH-548 | Feature List/Demo | 2 | Yes | Yes | NA |  |  | 5 | CHM / Video | No Dev
19 | AMXTECH-549 | Bandwidth Notification | 2 | No | No | NA |  |  | 4
20 | AMXTECH-550 | Test Connection | 2 | No | No | NA |  |  | 4
21 | AMXTECH-551 | Bhavcopy | 2 | No | No | NA |  |  | 8
22 | AMXTECH-552 | Tab name change and window | 2 | No | No | NA | Need to change once disign finalized |  | -
23 | AMXTECH-553 | Customize tool bar | 2 | No | No | NA |  |  | -
24 | AMXTECH-554 | Alerts on portfolio | 2 | Yes | Yes | NA |  |  | 8
25 | AMXTECH-555 | News | 2 | No | No | NA |  | 3rd Party | 7
26 | AMXTECH-556 | Buy and sell from News | 2 | Yes | Yes | NA |  | 3rd Party | 4
27 | AMXTECH-557 | Option Chain | 2 | Yes | Yes | NA |  |  | 7
28 | AMXTECH-558 | Pay-in and Pay-out | 2 | Yes | Yes | NA |  |  | 10
29 | AMXTECH-559 | Pivot Points | 2 | Yes | Yes | NA |  |  | 5
30 | AMXTECH-560 | Sector Wise Market Info | 2 | No | No | NA |  | 3rd Party | 10
31 | AMXTECH-561 | Deliveries ratio of scrips | 2 | No | No | NA |  | 3rd Party | 10
32 | AMXTECH-562 | Block Deals intimation only | 2 | No | No | NA |  | 3rd Party | 10

## Queries Pending at uTrade_AMX (hidden)
Sr No. | Modules / APIs | Description | Angel Remarks | Status | Responsibility | uTrade comments | Angel Remarks - 27Mar2019 | Angel Remarks - 04Apr2019 | Angel Remarks - 09May2019
1 | Order Flow | Two Cancellations are received for a single cancel through Alert Notifier. | We have reported this issue to OMNESYS | Open | Middleware - Angel | Will wait for the resolution | We are discussing with OMNESYS and get back to you
2 | Forgot Password | Forgot Password : SMS/Email Service is not functional at Angel end , due to which we could not test the same. | We will discussed internally and get back to you | Open | Product Team | Will wait for the resolution | We will discussed internally and get back to you
3 | Login | Multiple Logins allowed for same Client Id. | Application allow to login but not allow to perform any transaction or action. Application should display session expiry message as an when user login with same ID. | Open | Middleware - Angel | Discussion needed This should be handled at Angel-end. | It is under observation at angel end | It is under observation at angel end | Need to confirm with Dheeraj
4 | Exchange connectivity | Exchange connectivity status not received. | Connectivity status pop up display after login into application as disconnected, where as adapters are connected and we are able to place an orders. | Open | Product Team | We do not receive any Adapter connected status from the API. The exchange session message cannot be used for this purpose, as discussed earlier. | As discussed with product team, please remove exchange connectivity status window.
5 | 64 bit Lib | 64 bit Lib required: We tried compiling with the existing Lib but it didn't work. | We will discuss. As per our understanding existing will work on both. | Open | Middleware - Angel | This will work, but to increase the load capacity of the exe, 64 bit should be used. Let's plan in Phase-2 | We will discussed internally and get back to you | We will discussed internally and get back to you
6 | NCDEX | the precision we are receiving from GetAllSymbols API for NCDEX contracts is 2 always , which is not the case. We are getting precision other than 2 on our MCL/MDL module in some contracts. The contracts are as follows: COTTON16APR2019 : 0 (All COTTON contracts has precision 0.) BARLEYJPR16APR2019 : 1 (All BARLEYJPR contracts has precision 1.) SYOREF16APR2019 : 2 ( All SYOREF contracts has precision 2.) |  | Open | Middleware - Angel |  | We will discussed internally and get back to you | We will discussed internally and get back to you
7 | NCDEX | Unable to modify NCDEX order. Getting rejection text as : Error : Invalid custodian and/or account in OrderReport. |  | Open | Middleware - Angel |  | We will discussed internally and get back to you | We will discussed internally and get back to you
8 | NSE FO | Unable to place order in COL Order Validity (Field name Order Duration in Angel Place Order Structure). Receiving error of Invalid order duration from Angel Lib. |  | Open | Middleware - Angel |  | We will discussed internally and get back to you | We will discussed internally and get back to you
9 | PlaceMultiLegOrder API | whenever we provide negative price in PlaceMultiLegOrder API , the API call fails and gets stuck. |  | Open | Middleware - Angel
10 | GetAllSymbolResp API | For point Single ExpiryDate received in Spread Order in GetAllSymbolResp API , we discussed over call that this handling can be done at Angel Middle-ware end or at uTrade end as well. But from design point of view it'll make more sense to keep this handling at Angel Middle-ware end. Let me know in case of any concerns. |  | Open | Middleware - Angel